## Jun 12, 2023 21_12_43
Ticket ID | Ticket Summary | Ticket Repoter | Change Type | Changed From | Changed To
AN-10331 | Analysis rules - The evidence status isn't changing when a library rule toggle is turned on | Yarden Livne | resolution |  | Won't Do
|  |  | status | TO DO | WON'T DO
|  |  | Link |  | This issue relates to AN-9878
|  |  | labels | Analysis_rules | Analysis_rules unplanned
AN-10189 | Analysis rules - Filtering a recording with gap out will not filter the gap out | Yarden Livne | timeestimate |  | 0
|  |  | timespent |  | 28800
|  |  | WorklogId |  | 11132
|  |  | status | IN PROGRESS | STAGING
|  |  | labels | Analysis_rules unplanned | Analysis_rules
|  |  | Rank |  | Ranked lower
|  |  | Sprint | Integrations Sprint 3/Q2/23 | Integrations Sprint 4/Q2/23
|  |  | Rank |  | Ranked higher
|  |  | First Time In Progress |  | 09/Jun/23 3:25 PM
|  |  | Last Time In Progress |  | 09/Jun/23 3:25 PM
|  |  | Task Owner |  | Serhii Roh
|  |  | status | SELECTED FOR DEV | IN PROGRESS
|  |  | status | TO DO | SELECTED FOR DEV
|  |  | assignee | Aviram Raiffer | Serhii Roh
|  |  | Link |  | This issue relates to AN-9878
|  |  | labels | Analysis_rules | Analysis_rules unplanned
AN-10352 | Security Vulnerability in Ping feature | Michael Kipnis | RemoteIssueLink |  | This issue links to "Page (Confluence)"
|  |  | Epic Link |  | AN-10354
|  |  | IssueParentAssociation |  | AN-10354
|  |  | Link | This issue relates to AN-10354
|  |  | Link |  | This issue relates to AN-10354
|  |  | labels | Collaboration Security | Collaboration Security unplanned
|  |  | Sprint |  | Integrations Sprint 4/Q2/23
|  |  | priority | Medium | Highest
|  |  | labels |  | Collaboration Security
|  |  | Owner |  | Integrations
|  |  | assignee |  | Daniel Pollak
AN-10192 | Gitlab Self Managed - failed to collect all evidence | Mor Cohen | Last Time In Progress | 11/Jun/23 11:07 AM | 12/Jun/23 5:26 PM
|  |  | status | DESIGN REVIEW | IN PROGRESS
|  |  | assignee | Idan Arie | Sapir Ben Baz
|  |  | status | CR | DESIGN REVIEW
|  |  | assignee | Sapir Ben Baz | Idan Arie
|  |  | timeestimate | 0 | 0
|  |  | timespent |  | 28800
|  |  | WorklogId |  | 11129
|  |  | status | IN PROGRESS | CR
|  |  | First Time In Progress |  | 11/Jun/23 11:07 AM
|  |  | Last Time In Progress |  | 11/Jun/23 11:07 AM
|  |  | Task Owner |  | Sapir Ben Baz
|  |  | status | SELECTED FOR DEV | IN PROGRESS
|  |  | summary | Gitlab Self Manages - failed to collect all evidence | Gitlab Self Managed - failed to collect all evidence
|  |  | Rank |  | Ranked higher
|  |  | Initial Story Points |  | 1
|  |  | timeestimate |  | 0
|  |  | timeoriginalestimate |  | 28800
|  |  | Story Points |  | 1
|  |  | Link |  | This issue relates to AN-10225
|  |  | summary | Gitlab on prem- can't connect | Gitlab Self Manages - failed to collect all evidence
|  |  | Rank |  | Ranked higher
|  |  | Rank |  | Ranked higher
|  |  | assignee | Idan Arie | Sapir Ben Baz
|  |  | priority | Medium | High
|  |  | Rank |  | Ranked higher
|  |  | Sprint |  | Sprint 1 - Plugins
|  |  | status | TO DO | SELECTED FOR DEV
|  |  | labels |  | jira_escalated
|  |  | Owner | Integrations | Integrations,Plugins
AN-9860 | Policy manager - When owner is already set - The user can't set 'No owner'. | Helena Trubnikov | status | Dev Ready | STAGE READY
|  |  | Component |  | Policy Manager
|  |  | timeestimate |  | 28800
|  |  | timeoriginalestimate |  | 28800
|  |  | assignee | Shachar Cohen | Inbar Dor
|  |  | Rank |  | Ranked higher
|  |  | assignee | Tal Ovadia | Shachar Cohen
|  |  | Sprint | Apps sprint 16 | Apps sprint 15
|  |  | Sprint | Apps sprint 15 | Apps sprint 16
|  |  | Sprint | Apps sprint 14 | Apps sprint 15
|  |  | Sprint | Apps sprint 13 | Apps sprint 14
|  |  | status | TO DO | Dev Ready
|  |  | Sprint |  | Apps sprint 13
|  |  | Blocking Automated Test? |  | Blocking
AN-10237 | Tags - Collaborator user - the tags are clickable, but the user can't add/update/delete the tags | Helena Trubnikov | Component |  | Tags
|  |  | status | CR | STAGE READY
|  |  | status | IN PROGRESS | CR
|  |  | status | TO DO | IN PROGRESS
|  |  | timeestimate |  | 28800
|  |  | timeoriginalestimate |  | 28800
|  |  | assignee | Tal Ovadia | Inbar Dor
|  |  | Rank |  | Ranked higher
|  |  | Sprint | Apps sprint 16 | Apps sprint 15
|  |  | Sprint | Apps sprint 15 | Apps sprint 16
|  |  | Sprint |  | Apps sprint 15
|  |  | assignee | Hodaya Gor | Tal Ovadia
|  |  | Link |  | This issue relates to AN-9742
AN-10351 | UAR - Status not changed after new evidence collection when current status is Changes Required | Tal Ovadia | Component |  | Access Review
|  |  | status | CR | STAGE READY
|  |  | status | IN PROGRESS | CR
|  |  | status | TO DO | IN PROGRESS
|  |  | timeestimate |  | 7200
|  |  | timeoriginalestimate |  | 7200
|  |  | Rank |  | Ranked higher
|  |  | Sprint | Apps sprint 16 | Apps sprint 15
|  |  | Sprint |  | Apps sprint 16
|  |  | summary | Regression - UAR - Status not changed after new evidence collection when current status is Changes Required | UAR - Status not changed after new evidence collection when current status is Changes Required
|  |  | Environment |  | Staging
|  |  | summary | UAR - Status not changed after new evidence collection when current status is Changes Required | Regression - UAR - Status not changed after new evidence collection when current status is Changes Required
|  |  | Owner |  | Apps
AN-10323 | Github - Merged code changes evidence preview | Farouk Chemam | priority | High | Medium
|  |  | priority | Medium | High
|  |  | summary | Plugin - Github - Merged code changes | Github - Merged code changes evidence preview
|  |  | assignee |  | Idan Arie
AN-10273 | Customer Analytics - problem with policy status widgest | Niv Spektor | assignee | Niv Spektor | Eugene Shchur
|  |  | status | IN PROGRESS | DESIGN REVIEW
|  |  | status | TO DO | IN PROGRESS
|  |  | priority | Medium | High
|  |  | assignee |  | Niv Spektor
|  |  | Owner |  | solutions - data
AN-8993 | Risk manager - Notifications#3 - The treatment plan strategy status is not updated if redirected from the notification email | Helena Trubnikov | resolution |  | Done
|  |  | status | FEATURE TESTING | DONE
|  |  | assignee | Inbar Dor | Helena Trubnikov
|  |  | status | TO DO | FEATURE TESTING
|  |  | Link |  | This issue relates to AN-7941